## Sheet1
Date | Task Assigned | Status | Mentor | Completed Date
01.07.2019 | Angular Forms Concepts | Completed | Mehar | 01.07.2019
02.07.2019 | Static Login Form | Completed | Mehar | 02.07.2019
03.07.2019 | Login Form Using Routes and components | Completed | Mehar | 03.07.2019
04.07.2019 | Form Data save in an array in front end | Completed | Mehar | 04.07.2019
05.07.2019 | form validations using datepicker and moment.js | Completed | Mehar | 05.07.2019
08.07.2019 | navigate login form to Regform & store in backend | Completed | Mehar | 08.07.2019
09.07.2019 | Use ADD,EDIT,DELETE options in Regform table | Completed | Mehar | 09.07.2019
10.07.2019 | Use DatePicker,MultiSelect to RegForm and Knex server | Completed | Mehar | 10.07.2019
11.07.2019 | Using PrimeNG and date validations | primeng pending | Mehar
12.07.2019 | Using Joins and datepicker (DateofBirth and DateofJoining validations) | Completed | Mehar | 12.07.2019
15.07.2019 | Encryptiona and Decryption | Completed | Mehar | 15.07.2019
16.07.2019 | bootstrap-datepicker and validations | Completed | Mehar | 16.07.2019
17.07.2019 | Using My-date-picker (Startdate,Enddate and Range) | Completed | Prasad | 17.07.2019
18.07.2019 | full calendar (Add events) | Completed | Prasad,Rohith | 18.07.2019
19.07.2019 | Add & Delete forms using Form arrays | Completed | Prasad | 19.07.2019
22.07.2019 | Template Driven Forms with validations for ADD form | Completed | Mehar | 22.07.2019
23.07.2019 | Form Validations using ngModel &Fileupload | Completed | Mehar | 23.07.2019
24.07.2019 | Patchvalues of DOB,DOJ,Encryptdata save in backend | Encrypt pending | Mehar
25.07.2019 | Patchvalue of Multiselect(states),File Upload | Completed | Mehar | 25.07.2019
26.07.2019 | Add Profile Photo to RegistrationForm (file upload) | Completed | Mehar | 29.07.2019
29.07.2019 | Add Profile Photo to RegistrationForm (file upload) | Completed | Mehar | 29.07.2019
30.07.2019 | fullcalendar(prev,next buttons) | errors | Mehar
31.07.2019 | full calendar using different packages | errors | Mehar
01.08.2019 | Add more functionality to file upload and save in backend | Completed | Mehar | 01.08.2019
02.08.2019 | shift_order & shift_duration added to registration form | Completed | Mehar | 02.08.2019
05.08.2019 | HighCharts added to registration form(Gender&Date of Joining) | Completed | Mehar | 05.08.2019
06.08.2019 | HighCharts ,learn new things in angular | Completed | Mehar | 06.08.2019
07.08.2019 | Refresh all concepts again (I do Search and Ng2-export-as) | Completed | Mehar | 07.08.2019
08.08.2019 | Leave
09.08.2019 | Leave
10.08.2019 | Leave
12.08.2019 | Timepicker,Learning Basic Objection.js | Completed |  | 12.08.2019
13.08.2019 | Using Dropdown in Navigationbar